## Sheet1
Nonpublic Flexible Timeline for Equitable Services
New Fiscal Year Begins July 1st
The following activities are ongoing and should occur monthly, regularly or as needed throughout the fiscal year July 1 - June 30 to ensure the equitable services program is compliant and effective. The activities include but are not limited to... Monitoring/Site Visits for Title I, II, III and IV programs (monthly/as needed), third party contractors (as needed), professional development (as needed), and parent and family engagement(monthly) and ongoing consultation (as needed); Preparation and follow-up on budgets, contracts, requisitions, purchase orders, travel, payrolls, emails, calls, ongoing meaningful consultation and policy and guidance as needed.
MONTH | LEA ACTIVITY | ü | NOTES
July | Submit requisitions for allowable expenditures for equipment, materials, supplies, etc. for Titles I, II and IV
Submit third-party and professional contracts for the beginning of the next school year to the board for approval for Titles I, II and IV
Conduct status/update meeting with 3rd party contract personnel- scope/sequence review/update, interviews; process new hires, site visits
Check inventory, tag/label materials, equipment, etc.
Check status of contracts
Finalize Title I start date (Date should be the same as public school)
August | Start Title I, II, III, IV programs (Should start same date as public schools.)
Update Title I roster and add new students. Drop students who did not return or did not get parent's permission to participate.
Start student assessments
Start professional development and parent and family engagement
September - October | Send the Non-public Family Income Survey or get official Free and Reduced Lunch Reports from non-public schools to get October 1st counts to calculate the non-public Title I allocation for the LEA Title I Non-public Program. Provide a 2 to 3 week turnaround time and deadline date.
LEAs may send the Intent to Participate Form to non-public schools with the Non-public Family Income Survey to pre - determine which non-public schools would like to participate or decline equitable services for next school year.
Review Non-public Family Income Surveys and determine which forms are from low - socioeconomic households and count the qualifying forms to get the October 1st count. File all qualifying and non-qualifying (middle and higher family income statuses) in separate sealed envelopes in locked filing cabinet for equitable services confidential information.
November - January | Complete competitive portion of the Super App. Release 2022-2023 Super App (November 1, 2021)
Start preparation for next school year for Titles I, II, III and IV equitable services.
Obtain Non-public Academic Classification /Brumfield v Dodd list of all private schools approved by BESE. (Ombudsman will send unofficial list in December and official list in January)
Print out current Non-public Academic Classification/Brumfield v Dodd list of all private schools in your LEA district.
Contact private schools that are on the Non-public Academic Classification/Brumfield v Dodd approved list, new private schools, and for-profit organizations to see if their status has changed and offer services if the schools have a non-profit status.
Notify Schools for Free and Reduced Lunch count for October 1. Request physical address for FRL students to determine participating attendance zone.
January - February | Set-up timeline/schedule for contacting private schools for the Initial Timely Meaningful Consultation Meeting for the next school year.
Prepare “Intent to Participate Letter” to send out for eligible private schools from the Brumfield vs Dodd list to offer Titles I, II, III, IV and 21st Century services for next school year. You may also include: Affirmation of Consultation and Agreement for initial timely and meaningful consultation
School systems submit applications to LDOE for review (February 2022)
Send “Letter of Intent to Participate” (provide private schools a 2 - 3 week turnaround and deadline date)
Send letter certified mail; make sure you have documentation for monitoring that the letter/documents were sent out. Also fax and email the letter as well for monitoring documentation.
Keep returned documents in confidential space (locked cabinet) and document when the items above are returned.
Contact schools that you have not received a response after two weeks to remind them and provide the deadline date
Inform private schools of their budget balances and deadlines for processing contracts, requisitions/purchase orders, travel, budget amendments, etc., via ongoing meaningful consultation (Note: Include a June 30 deadline and consult with private schools if carryover may be required. During consultation clearly explain the FIFO method in which, all carryover allocations must be used first before current years allocations can be expended.
February - March | Collect/document certified mail cards, Affirmations of Consultation, Family Income Surveys, Letters of Intent to Participate, etc.
Process/document Family Income Surveys/ Free and Reduced Lunch List (check attendance zone and school counts)
Put poverty/income data in a spreadsheet to use for eGMS Title I allocation calculations
LDOE approved competitive portion of 2022-23 Super App
Monitoring/Site Visits –Titles I, II, III, and IV programs, third party contractors, professional development, parent and family engagement, etc.
Prepare and follow-up on budgets, contracts, requisitions, purchase orders, travel, payrolls, emails, calls, ongoing meaningful consultation and policy/guidance
March - April | Prepare for release of preliminary formula funding and competitive funding after April BESE approval.
Prepare materials/folders, PowerPoint/Webinar, etc., for initial timely and meaningful consultation informational meeting for next school year; schedule room, etc.
Prepare materials/folders, PowerPoint/Webinar, etc., for initial timely and meaningful consultation informational meeting for next school year; schedule room, etc.
Send a save the date or reminder 1 week, as well as, 2 days before the meeting
Complete application in eGMS
April - June | Collect multiple academic criteria data to use for selecting eligible private school students for Title I next year: standardize test data, math and reading report card grades, teacher ranking forms, other assessment data, student work samples (optional), etc.
Collect parent and family engagement and professional development surveys, evaluation and data for end of the year evaluation
Program evaluations (assess annual progress through standardized test data by comparing last year’s data to this year’s data, surveys [teachers, Title I Teachers, administrators, parents and students], online tutorial program assessment data, etc.
Design or update the LEA Non-public Title I program. Make adjustments or changes based on standardized test/curriculum data/information, other assessments data, ongoing consultations, and budgets, etc.
Begin the requisition process to order materials, supplies and equipment for next school year
Conduct inventory of fixed assets (items $5,000 and over) and Title I general inventory of materials, supplies, items under $5,000.00. Request a list of inventory and location/room number on campus.
Send reminder letter to private schools regarding budgets, rollover, June 30 deadline, carryover, etc.
Conduct initial meaningful and timely consultation meeting for next school year and obtain signatures for Affirmation of Consultations
Set-up appointments for follow- up meaningful consultation meetings
Document private school input and work applicable items into Titles I, II, III, IV plans, eGMS/budgets, etc.
Finalize third party contracts for Title I, and contacts for Title II and Title IV, professional development, instructional services, parent and family engagement, etc. for the next school year. (Note: Private school services should start at the same time as public school services.)
Review student referrals for Title I participants; review for eligibility and attendance area. Finalize student data, roster, etc.
Update private schools on any programs changes or updates
Meet with 3rd party contractors to discuss instructional program and timeline
Work with technology dept. to ensure desktops, laptops, iPads, Chromebooks are operational for the beginning of the school year
Provide Title I Summer School, if applicable
Fiscal Year Ends June 30th; Rollover Ends June 30th; Carryover is determined as of September 30th (complete and upload Carryover Form to eGMS if needed)